## Project Plan
INTELLIDRAFT — Project Plan & Timeline
Start: 01-Jun-2026 ¦ Est. Completion: 14-Sep-2026 ¦ Remaining: ~61.5 working days ¦ Generated: 30-May-2026
# | Phase | Task ID | Task Name | Description | Est. Days | Start Date | End Date | Work Days | Status | Dependencies | Notes
PHASE 0 — Core Engine (Completed)
1 | Ph.0 — Core Engine | 0.1 | Document Parsers | PDF, DOCX, PPTX, Excel — text, tables, images extraction | 5 | 2026-06-01 | 2026-06-05 |  | Completed | —
2 | Ph.0 — Core Engine | 0.2 | Vision Analyzer | Image type detection & description via LLM | 2 | 2026-06-08 | 2026-06-09 |  | Completed | 0.1
3 | Ph.0 — Core Engine | 0.3 | Storage Layer | Local filesystem + Azure Blob/Cosmos DB dual-mode | 3 | 2026-06-10 | 2026-06-12 |  | Completed | —
4 | Ph.0 — Core Engine | 0.4 | Generation DB Schema | SQLAlchemy ORM, SQLite (dev) / Azure SQL (prod) toggle | 1 | 2026-06-15 | 2026-06-15 |  | Completed | —
5 | Ph.0 — Core Engine | 0.5 | Prompt Template System | BRD, RFP, SOW, Proposal, TechSpec, Scope templates | 2 | 2026-06-16 | 2026-06-17 |  | Completed | 0.4
6 | Ph.0 — Core Engine | 0.6 | Section Generator | LLM call per section, revision mode, GPT-5 compatible | 2 | 2026-06-18 | 2026-06-19 |  | Completed | 0.5
7 | Ph.0 — Core Engine | 0.7 | Generation Service | Job orchestration, background threading, status tracking | 2 | 2026-06-22 | 2026-06-23 |  | Completed | 0.6
8 | Ph.0 — Core Engine | 0.8 | Document Writer | DOCX / PDF / Markdown export with Markdown renderer | 2 | 2026-06-24 | 2026-06-25 |  | Completed | 0.7
9 | Ph.0 — Core Engine | 0.9 | Basic Flask API | Upload, extract, generate, export endpoints + CORS | 3 | 2026-06-26 | 2026-06-30 |  | Completed | 0.3, 0.4
PHASE 1 — Backend API Completion
10 | Ph.1 — Backend API | 1.1 | Authentication Middleware | API key or Azure AD token validation on all routes | 2 | 2026-07-01 | 2026-07-02 |  | Not Started | —
11 | Ph.1 — Backend API | 1.2 | Document Management API | List all documents, delete document and stored files | 1 | 2026-07-03 | 2026-07-03 |  | Not Started | 0.3
12 | Ph.1 — Backend API | 1.3 | Project Management API | Create/list/delete projects, attach documents to project | 1.5 | 2026-07-06 | 2026-07-07 |  | Not Started | 0.4
13 | Ph.1 — Backend API | 1.4 | Template CRUD API | Create/edit/delete user-defined templates via API | 1.5 | 2026-07-08 | 2026-07-09 |  | Not Started | 0.5
14 | Ph.1 — Backend API | 1.5 | Section Review API | Submit edit comment, approve section, trigger re-generation | 1.5 | 2026-07-10 | 2026-07-13 |  | Not Started | 0.7
15 | Ph.1 — Backend API | 1.6 | Input Validation & Errors | Pydantic models, structured 400/422 error responses | 1 | 2026-07-14 | 2026-07-14 |  | Not Started | —
16 | Ph.1 — Backend API | 1.7 | Rate Limiting | Per-IP or per-API-key throttle on upload & generate | 0.5 | 2026-07-15 | 2026-07-15 |  | Not Started | 1.1
17 | Ph.1 — Backend API | 1.8 | OpenAPI / Swagger Docs | Auto-generated API documentation from Flask routes | 1 | 2026-07-16 | 2026-07-16 |  | Not Started | 1.1–1.6
PHASE 2 — Frontend UI
18 | Ph.2 — Frontend UI | 2.1 | Generation Progress Page | Real-time section status via polling, per-section progress bars | 2 | 2026-07-17 | 2026-07-20 |  | Not Started | 0.9
19 | Ph.2 — Frontend UI | 2.2 | Section Viewer | Display all generated sections, collapsible panels | 2 | 2026-07-21 | 2026-07-22 |  | Not Started | 2.1
20 | Ph.2 — Frontend UI | 2.3 | Inline Section Editor | Click-to-edit section content, save back to DB | 3 | 2026-07-23 | 2026-07-27 |  | Not Started | 2.2, 1.5
21 | Ph.2 — Frontend UI | 2.4 | Comment & Revision Workflow | Submit edit request, LLM rewrite, side-by-side diff view | 3 | 2026-07-28 | 2026-07-30 |  | Not Started | 2.3
22 | Ph.2 — Frontend UI | 2.5 | Section Approval UI | Approve / reject buttons per section | 1 | 2026-07-31 | 2026-07-31 |  | Not Started | 2.4
23 | Ph.2 — Frontend UI | 2.6 | Export Download UI | DOCX / PDF / Markdown download buttons with status | 1 | 2026-08-03 | 2026-08-03 |  | Not Started | 0.8
24 | Ph.2 — Frontend UI | 2.7 | Template Selector | Dropdown on generate form with section list preview | 1.5 | 2026-08-04 | 2026-08-05 |  | Not Started | 1.4
25 | Ph.2 — Frontend UI | 2.8 | Template Editor UI | Create / edit custom templates from the browser | 2 | 2026-08-06 | 2026-08-07 |  | Not Started | 1.4
26 | Ph.2 — Frontend UI | 2.9 | Project History Page | List past generation jobs, reopen, re-download outputs | 2 | 2026-08-10 | 2026-08-11 |  | Not Started | 1.3
27 | Ph.2 — Frontend UI | 2.10 | Document Library Page | List uploaded documents, delete, re-parse | 1.5 | 2026-08-12 | 2026-08-13 |  | Not Started | 1.2
28 | Ph.2 — Frontend UI | 2.11 | Responsive Design | Mobile-friendly layout across all pages | 2 | 2026-08-14 | 2026-08-17 |  | Not Started | 2.1–2.9
29 | Ph.2 — Frontend UI | 2.12 | Loading States & Error Handling | Global toasts, spinners, error boundaries | 1.5 | 2026-08-18 | 2026-08-19 |  | Not Started | 2.1–2.10
PHASE 3 — Testing ★ Runs in Parallel with Phase 2
30 | Ph.3 — Testing | 3.1 | Unit Tests — Parsers | PDF, DOCX, PPTX, Excel edge cases and regression tests | 2 | 2026-07-17 | 2026-07-20 |  | Not Started | 0.1
31 | Ph.3 — Testing | 3.2 | Unit Tests — Generator | Mock LLM, token budget logic, threading tests | 2 | 2026-07-21 | 2026-07-22 |  | Not Started | 0.6, 0.7
32 | Ph.3 — Testing | 3.3 | Unit Tests — Doc Writer | DOCX table rendering, PDF fallback chain tests | 1 | 2026-07-23 | 2026-07-23 |  | Not Started | 0.8
33 | Ph.3 — Testing | 3.4 | Integration Tests — API | Full upload → extract → generate → export flow | 2 | 2026-07-24 | 2026-07-27 |  | Not Started | Phase 1
34 | Ph.3 — Testing | 3.5 | E2E Tests — Browser | Playwright or Selenium end-to-end browser tests | 2 | 2026-08-20 | 2026-08-21 |  | Not Started | Phase 2
35 | Ph.3 — Testing | 3.6 | LLM Prompt Regression Tests | Golden output comparisons, word count checks | 1.5 | 2026-08-20 | 2026-08-21 |  | Not Started | 0.6
PHASE 4 — Azure Infrastructure ★ Runs in Parallel with Phase 2
36 | Ph.4 — Azure Infra | 4.1 | Azure Resource Group | Subscription, resource group, naming conventions, IAM | 0.5 | 2026-07-17 | 2026-07-17 |  | Not Started | —
37 | Ph.4 — Azure Infra | 4.2 | Azure SQL Database | Create, configure firewall, run schema migration from SQLite | 1 | 2026-07-20 | 2026-07-20 |  | Not Started | 0.4
38 | Ph.4 — Azure Infra | 4.3 | Azure Blob Storage | Container setup, CORS policy, SAS token configuration | 0.5 | 2026-07-21 | 2026-07-21 |  | Not Started | 0.3
39 | Ph.4 — Azure Infra | 4.4 | Azure Cosmos DB | Account, database, container, partition key setup | 0.5 | 2026-07-22 | 2026-07-22 |  | Not Started | 0.3
40 | Ph.4 — Azure Infra | 4.5 | Azure OpenAI / GPT-5 | Model deployment, quota request, endpoint configuration | 1 | 2026-07-23 | 2026-07-23 |  | Not Started | —
41 | Ph.4 — Azure Infra | 4.6 | Azure Key Vault | Store all secrets: API keys, connection strings, certs | 0.5 | 2026-07-24 | 2026-07-24 |  | Not Started | 4.1
42 | Ph.4 — Azure Infra | 4.7 | Application Insights | Logging, distributed traces, live metrics dashboard | 0.5 | 2026-07-27 | 2026-07-27 |  | Not Started | 4.1
43 | Ph.4 — Azure Infra | 4.8 | Environment Config Files | .env.dev, .env.staging, .env.prod with all variables | 0.5 | 2026-07-28 | 2026-07-28 |  | Not Started | 4.1–4.7
PHASE 5 — Deployment & CI/CD
44 | Ph.5 — Deployment | 5.1 | Dockerize Backend | Dockerfile, .dockerignore, docker-compose for local dev | 1 | 2026-08-24 | 2026-08-24 |  | Not Started | Phase 1
45 | Ph.5 — Deployment | 5.2 | Azure Function App Deployment | Backend API on Azure Functions consumption plan | 1.5 | 2026-08-25 | 2026-08-26 |  | Not Started | 5.1, Phase 4
46 | Ph.5 — Deployment | 5.3 | Azure Static Web Apps | Frontend hosting, custom domain, HTTPS certificate | 1 | 2026-08-27 | 2026-08-27 |  | Not Started | Phase 2
47 | Ph.5 — Deployment | 5.4 | GitHub Actions CI Pipeline | Lint, test, build triggered on every pull request | 1.5 | 2026-08-28 | 2026-08-31 |  | Not Started | Phase 3
48 | Ph.5 — Deployment | 5.5 | GitHub Actions CD Pipeline | Auto-deploy to staging on merge to main branch | 1 | 2026-09-01 | 2026-09-01 |  | Not Started | 5.2, 5.3, 5.4
49 | Ph.5 — Deployment | 5.6 | Staging Deployment & Smoke Tests | Full environment validation + end-to-end smoke suite | 1 | 2026-09-02 | 2026-09-02 |  | Not Started | 5.5
50 | Ph.5 — Deployment | 5.7 | Production Deployment | Blue/green cutover to production environment | 0.5 | 2026-09-03 | 2026-09-03 |  | Not Started | 5.6
PHASE 6 — Production Hardening
51 | Ph.6 — Hardening | 6.1 | Security Review | OWASP top 10, secret scanning, dependency vulnerability audit | 1 | 2026-09-04 | 2026-09-04 |  | Not Started | Phase 5
52 | Ph.6 — Hardening | 6.2 | Performance Tuning | Async generation, DB query optimization, response caching | 1.5 | 2026-09-07 | 2026-09-08 |  | Not Started | Phase 5
53 | Ph.6 — Hardening | 6.3 | Monitoring & Alerts | App Insights dashboards, failure & cost budget alerts | 1 | 2026-09-09 | 2026-09-09 |  | Not Started | 4.7
54 | Ph.6 — Hardening | 6.4 | Backup & Recovery | Azure SQL auto-backups, blob versioning policy | 0.5 | 2026-09-10 | 2026-09-10 |  | Not Started | Phase 4
55 | Ph.6 — Hardening | 6.5 | Developer Documentation | README, API reference, architecture guide, deployment runbook | 1 | 2026-09-11 | 2026-09-11 |  | Not Started | Phase 5
56 | Ph.6 — Hardening | 6.6 | User Documentation | How-to guide: uploading, generating, editing, exporting | 1 | 2026-09-14 | 2026-09-14 |  | Not Started | Phase 2
Formulas:
Work Days = NETWORKDAYS([Start Date],[End Date])

## Summary
INTELLIDRAFT — Project Summary by Phase
Project Start: 01-Jun-2026 ¦ Estimated End: 14-Sep-2026 ¦ Total Duration: ~4 months
# | Phase | Tasks | Est. Days | Start Date | End Date | Track | Status | Notes
0 | PHASE 0 — Core Engine (Completed) | 9 | 22 | 2026-06-01 | 2026-06-30 | Sequential | ✅ Completed | Foundational engine — all done
1 | PHASE 1 — Backend API Completion | 8 | 10 | 2026-07-01 | 2026-07-16 | Sequential | 🔲 Not Started | Auth, CRUD APIs, validation, Swagger
2 | PHASE 2 — Frontend UI | 12 | 22.5 | 2026-07-17 | 2026-08-19 | Sequential | 🔲 Not Started | Full UI — editor, viewer, export, history
3 | PHASE 3 — Testing ★ Runs in Parallel with Phase 2 | 6 | 10.5 | 2026-07-17 | 2026-08-21 | ⟵ Parallel with Ph.2 | 🔲 Not Started | Unit, integration, E2E, LLM regression
4 | PHASE 4 — Azure Infrastructure ★ Runs in Parallel with Phase 2 | 8 | 5 | 2026-07-17 | 2026-07-28 | ⟵ Parallel with Ph.2 | 🔲 Not Started | All Azure cloud resources provisioned
5 | PHASE 5 — Deployment & CI/CD | 7 | 7.5 | 2026-08-24 | 2026-09-03 | Sequential (after 2,3,4) | 🔲 Not Started | Docker, CI/CD pipelines, staging, prod
6 | PHASE 6 — Production Hardening | 6 | 6 | 2026-09-04 | 2026-09-14 | Sequential | 🔲 Not Started | Security, performance, monitoring, docs
| TOTAL REMAINING (Phase 1–6) | 47 | ~61.5 days
CRITICAL PATH — Minimum to First Production Release
Phase | Description | Start | End | Est. Days | Parallel?
Phase 1 | Backend API Completion | 2026-07-01 | 2026-07-16 | 10 | No
Phase 2 | Frontend UI | 2026-07-17 | 2026-08-19 | 22.5 | No
Phase 3 | Testing | 2026-07-17 | 2026-08-21 | 10.5 | Yes — alongside Ph.2
Phase 4 | Azure Infrastructure | 2026-07-17 | 2026-07-28 | 5 | Yes — alongside Ph.2
Phase 5 | Deployment & CI/CD | 2026-08-24 | 2026-09-03 | 7.5 | No
Phase 6 | Production Hardening | 2026-09-04 | 2026-09-14 | 6 | No
NOTE: Phase 3 (Testing) and Phase 4 (Azure Infra) run in parallel with Phase 2 (Frontend) to reduce total calendar time by ~3 weeks.

## Gantt View
INTELLIDRAFT — Gantt View (Weekly)
|  |  |  | Jun 2026 |  |  |  |  | Jul 2026 |  |  |  | Aug 2026 |  |  |  |  | Sep 2026
Task ID | Task Name | Phase | Days | 01 | 08 | 15 | 22 | 29 | 06 | 13 | 20 | 27 | 03 | 10 | 17 | 24 | 31 | 07 | 14 | 21
PHASE 0 — Core Engine (Completed)
0.1 | Document Parsers | Ph.0 — Core Engine | 5
0.2 | Vision Analyzer | Ph.0 — Core Engine | 2
0.3 | Storage Layer | Ph.0 — Core Engine | 3
0.4 | Generation DB Schema | Ph.0 — Core Engine | 1
0.5 | Prompt Template System | Ph.0 — Core Engine | 2
0.6 | Section Generator | Ph.0 — Core Engine | 2
0.7 | Generation Service | Ph.0 — Core Engine | 2
0.8 | Document Writer | Ph.0 — Core Engine | 2
0.9 | Basic Flask API | Ph.0 — Core Engine | 3
PHASE 1 — Backend API Completion
1.1 | Authentication Middleware | Ph.1 — Backend API | 2
1.2 | Document Management API | Ph.1 — Backend API | 1
1.3 | Project Management API | Ph.1 — Backend API | 1.5
1.4 | Template CRUD API | Ph.1 — Backend API | 1.5
1.5 | Section Review API | Ph.1 — Backend API | 1.5
1.6 | Input Validation & Errors | Ph.1 — Backend API | 1
1.7 | Rate Limiting | Ph.1 — Backend API | 0.5
1.8 | OpenAPI / Swagger Docs | Ph.1 — Backend API | 1
PHASE 2 — Frontend UI
2.1 | Generation Progress Page | Ph.2 — Frontend UI | 2
2.2 | Section Viewer | Ph.2 — Frontend UI | 2
2.3 | Inline Section Editor | Ph.2 — Frontend UI | 3
2.4 | Comment & Revision Workflow | Ph.2 — Frontend UI | 3
2.5 | Section Approval UI | Ph.2 — Frontend UI | 1
2.6 | Export Download UI | Ph.2 — Frontend UI | 1
2.7 | Template Selector | Ph.2 — Frontend UI | 1.5
2.8 | Template Editor UI | Ph.2 — Frontend UI | 2
2.9 | Project History Page | Ph.2 — Frontend UI | 2
2.10 | Document Library Page | Ph.2 — Frontend UI | 1.5
2.11 | Responsive Design | Ph.2 — Frontend UI | 2
2.12 | Loading States & Error Handling | Ph.2 — Frontend UI | 1.5
PHASE 3 — Testing ★ Runs in Parallel with Phase 2
3.1 | Unit Tests — Parsers | Ph.3 — Testing | 2
3.2 | Unit Tests — Generator | Ph.3 — Testing | 2
3.3 | Unit Tests — Doc Writer | Ph.3 — Testing | 1
3.4 | Integration Tests — API | Ph.3 — Testing | 2
3.5 | E2E Tests — Browser | Ph.3 — Testing | 2
3.6 | LLM Prompt Regression Tests | Ph.3 — Testing | 1.5
PHASE 4 — Azure Infrastructure ★ Runs in Parallel with Phase 2
4.1 | Azure Resource Group | Ph.4 — Azure Infra | 0.5
4.2 | Azure SQL Database | Ph.4 — Azure Infra | 1
4.3 | Azure Blob Storage | Ph.4 — Azure Infra | 0.5
4.4 | Azure Cosmos DB | Ph.4 — Azure Infra | 0.5
4.5 | Azure OpenAI / GPT-5 | Ph.4 — Azure Infra | 1
4.6 | Azure Key Vault | Ph.4 — Azure Infra | 0.5
4.7 | Application Insights | Ph.4 — Azure Infra | 0.5
4.8 | Environment Config Files | Ph.4 — Azure Infra | 0.5
PHASE 5 — Deployment & CI/CD
5.1 | Dockerize Backend | Ph.5 — Deployment | 1
5.2 | Azure Function App Deployment | Ph.5 — Deployment | 1.5
5.3 | Azure Static Web Apps | Ph.5 — Deployment | 1
5.4 | GitHub Actions CI Pipeline | Ph.5 — Deployment | 1.5
5.5 | GitHub Actions CD Pipeline | Ph.5 — Deployment | 1
5.6 | Staging Deployment & Smoke Tests | Ph.5 — Deployment | 1
5.7 | Production Deployment | Ph.5 — Deployment | 0.5
PHASE 6 — Production Hardening
6.1 | Security Review | Ph.6 — Hardening | 1
6.2 | Performance Tuning | Ph.6 — Hardening | 1.5
6.3 | Monitoring & Alerts | Ph.6 — Hardening | 1
6.4 | Backup & Recovery | Ph.6 — Hardening | 0.5
6.5 | Developer Documentation | Ph.6 — Hardening | 1
6.6 | User Documentation | Ph.6 — Hardening | 1